## Gantchart
GANTT CHART Mini Project | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE - Student Result Processing System | [6 empty] | DEPARTMENT NAME - Iinformation Technology
PROJECT GUIDE - Prof. Apeksha Mohite | [6 empty] | DATE | [6 empty] | 2021-12-14
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [24 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
WEEK 1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Neha Chaudhary Kritika Donde Sakshi Gunjal Ashmina Dangat | 2021-09-16 | 2021-09-23 | 2 | 100% | bar: WEEK 1 F to WEEK 2 F
WEEK 2 | Identifying the technology stack and functionalities of the Mini Project | Neha Chaudhary Kritika Donde Sakshi Gunjal Ashmina Dangat | 9-21-21 | 9-30-21 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F
WEEK 3 | Discussing the project topic with the help of paper prototype. | Neha Chaudhary Kritika Donde Sakshi Gunjal Ashmina Dangat | 2021-01-10 | 2021-10-10 | 1 | 100% | bar: WEEK 2 W to WEEK 3 W
WEEK 4 | Presentation I | Ashmina Dangat Sakshi Gunjal Neha Chaudhary Kritika Donde | 2021-11-10 | 10-19-21 | 1 | 100% | bar: WEEK 2 W to WEEK 3 R
2 | Project Design and Implementation
WEEK 5 | Designing the Graphical User Interface(GUI) | Neha Chaudhary Kritika Donde Sakshi Gunjal Ashmina Dangat | 2021-10-10 | 10-26-21 | 2 | 100% | bar: WEEK 2 W to WEEK 3 R
WEEK 6 | Database Design | Ashmina Dangat Sakshi Gunjal Neha Chaudhary Kritika Donde | 2021-10-03 | 2021-10-10 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 M to WEEK 4 R
WEEK 7 | Database Connectivity with front end | Ashmina Dangat Sakshi Gunjal Neha Chaudhary Kritika Donde | 2021-11-11 | 11-20-21 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 F to WEEK 5 F
WEEK 8 | Results and Report Writing | Ashmina Dangat Sakshi Gunjal Neha Chaudhary Kritika Donde | 11-21-21 | 11-24-21 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 6 M to WEEK 7 F
WEEK 9 | Presentation II | Ashmina Dangat Sakshi Gunjal Neha Chaudhary Kritika Donde | 11-25-21 | 2021-02-12 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 8 M to WEEK 9 F